## Dashboard
WEDDING PLANNING CHECKLIST
Enter your wedding date once — every due date fills itself in.
YOUR WEDDING DATE | 2027-06-12
↑ the only cell you must fill in (blue text = your input)
PROGRESS
Days until the wedding
Tasks complete
Tasks total
Percent complete
Overdue & not done
Due in the next 30 days
BY STAGE
Stage | Done | Of
12+ months before
9-11 months before
6-8 months before
4-5 months before
2-3 months before
1 month before
1 week before
Due dates are calculated back from your wedding date and are a normal planning cadence, not a rule. Move any of them.
Free wedding spreadsheets, no email required — https://kitelabs.netlify.app/
Free to use and share. Not for resale.

## Checklist
CHECKLIST
Tick things off in the "Status" column. Overdue rows turn red on their own.
Stage | Task | Lead time | Due date | Status | Who | Notes
12+ months before | Set your total budget | 365 |  | Done | Both | Example row — type over it
12+ months before | Pick your wedding date | 355 |  | Not started
12+ months before | Book your venue | 344 |  | Not started
12+ months before | Start a guest list draft | 333 |  | Not started
12+ months before | Research & book a wedding planner (optional) | 322 |  | Not started
9-11 months before | Book photographer & videographer | 300 |  | Not started
9-11 months before | Choose your officiant | 291 |  | Not started
9-11 months before | Send save-the-dates | 282 |  | Not started
9-11 months before | Start dress/suit shopping | 273 |  | Not started
9-11 months before | Book caterer (if separate from venue) | 264 |  | Not started
6-8 months before | Book music/DJ or band | 210 |  | Not started
6-8 months before | Book florist | 204 |  | Not started
6-8 months before | Order invitations | 198 |  | Not started
6-8 months before | Book hair & makeup trial | 192 |  | Not started
6-8 months before | Plan honeymoon | 185 |  | Not started
4-5 months before | Order wedding rings | 140 |  | Not started
4-5 months before | Finalize menu & cake tasting | 136 |  | Not started
4-5 months before | Book transportation | 132 |  | Not started
4-5 months before | Buy accessories & shoes | 128 |  | Not started
4-5 months before | Arrange guest accommodations | 124 |  | Not started
2-3 months before | Send invitations | 75 |  | Not started
2-3 months before | Finalize seating chart draft | 73 |  | Not started
2-3 months before | Schedule dress/suit fittings | 71 |  | Not started
2-3 months before | Confirm all vendor details in writing | 69 |  | Not started
2-3 months before | Apply for marriage license | 66 |  | Not started
1 month before | Final guest count to caterer | 30 |  | Not started
1 month before | Final dress/suit fitting | 30 |  | Not started
1 month before | Confirm timeline with all vendors | 29 |  | Not started
1 month before | Prepare final payments & tips | 28 |  | Not started
1 month before | Break in wedding shoes | 27 |  | Not started
1 week before | Confirm arrival times with vendors | 7 |  | Not started
1 week before | Delegate day-of tasks | 7 |  | Not started
1 week before | Pack for honeymoon | 7 |  | Not started
1 week before | Give final headcount & seating chart to venue | 7 |  | Not started
1 week before | Relax — you're ready! | 7 |  | Not started
"Lead time" is days before the wedding. Change a lead time and the due date moves with it.